## Run Plan
2015-10-22 23:00 |  | Goals of 1st commission run
2015-10-23 11:00 |  | Operating TPC with beam
Test Gating Grid
Take data with TPC
setup auxiliary detectors
Analog and discriminator signals for Start, Active collimator, 2 upstream scintillators and veto routed out (16 signals).
TTL_Open and TTLClose disconnected (?) from GG driver.
0.1 mm Sn target
Personnel | I_beam | time | duration | Tasks
Tetsuya/Isobe | 2015-10-22 | 23:00 | 0:30 | check beam rate on Samurai beam plastic before TPC
Tetsuya/Isobe | any | 23:30 | 1:00 | transport beam to TPC and check tuning, turn on voltages of auxiliary devices w/o remote control
Bill/Jon/Justin | any | 24:30 | 1:00 | set voltages and thresholds on scintillator (2-3 iterations)
Bill/Jon/Justin | No beam | 25:30 | 0:30 | estimate misalignment and need to move Katana & TPC
Bill/Jon/Justin | No beam | 26:00 | 0:30 | retune if necessary (change B field, adjust last quad??)
Bill/Jon/Justin | <10 Hz | 26:30 | 1:00 | Slowly raise the voltages on the anodes (<10 Hz)
Bill/Jon/Justin | <10 Hz | 27:30 | 1:00 | data run at mid range of TPC, check beam profile and beam space charge ??
Hyo Sang/Justin/Bill | <10 Hz | 28:30 | 0:30 | Varying the Gating Grid Voltage
Hyo Sang/Justin/Bill | <10 Hz | 29:00 | 0:30 | https://docs.google.com/spreadsheets/d/1UAeDEBw7f1Zr9flBgYRSoDCEhSVmlDeXVp7POSwwoAI/edit#gid=0
Hyo Sang/Justin/Bill | <10 Hz | 29:30 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 30:00 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 30:30 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 31:00 | 0:30 | Raise the anode voltage to the operating voltage. Check again?
Polish group | Max | 31:30 | 1:00 | Check trigger logic
Piotr/Bill | Max | 32:30 | 0:30 | Put trigger into standard mode so that we suppress non-interacted beam.
Jon/Mizuki/Clementine | Max | 33:00 | 0:30 | change to aluminum brick target
Piotr/Bill | Max | 33:30 | 1:30 | Take a long run on the Al “brick” target.
| Max | 35:00 |  | give beam back to IMPACT
Hyo Sang/Justin |  |  | 20 | pulser ramp

## Shifts
SHIFT
Shifts | 22:00 |  |  | 22:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Genie
|  | Manpower |  | 23:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Genie
|  | beam | Isobe/Mizuki/Suzuki | 24:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Genie
|  | start/veto scintillator | Clementine | 25:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Genie
|  | Katana | Jerzy/Pawel/Piotr/Krzysztof | 26:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Genie
|  | Kyoto Array | Tetsuya/Keneko | 27:00 | Isobe |  |  | Lynch |  | Hyo Sang |  | Genie
|  | Active Veto | Yan Zhang | 28:00 | Isobe |  |  | Lynch |  | Hyo Sang |  | Genie
|  | TPC | Lynch/Jon/Clementine | 29:00 | Mizuki | suzuki |  | Lynch |  | Hyo Sang |  | Giordano
Shift leader |  | GG | Lee/Justin/Lynch | 30:00 | Mizuki | suzuki |  |  |  | Hyo Sang |  | Giordano
|  | software | Genie/Giordano | 31:00 | Mizuki | suzuki |  |  |  | Hyo Sang |  | Giordano
|  | Shift Leader | Betty/Mizuki | 32:00 | Mizuki | suzuki |  |  |  | Hyo Sang |  | Giordano
|  |  |  | 33:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang |  | Giordano
|  |  |  | 34:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang |  | Giordano
|  |  |  | 35:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang |  | Giordano
|  |  |  | 36:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang |  | Giordano
|  |  |  | 37:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang |  | Giordano
41:00
42:00
43:00
44:00
45:00
46:00
47:00
48:00
49:00
50:00
51:00
52:00
53:00
54:00
55:00
56:00
57:00
58:00
59:00
60:00