## Round 2!
Date | Object | DAQ&Software | BigRIPS/Japanese | Electronics |  | Katana | GG | Shifts by initials
2016-04-08 19:00 | MT for Ota-san (bean tuning with STQ25) move Katana | Giordano | Isobe |  |  |  |  | MK WL CS GC YZ JB PP TI BT GJ JE | Name | Code
4/8/2016 20:00:00 | MT for Ota-san (bean tuning with STQ25) | Giordano | Isobe |  |  |  |  | MK WL CS GC YZ JB PP TI BT GJ JE | Barney | JB
4/8/2016 21:00:00 | Make sure tuning is good and clean |  | Isobe | Lynch | Clem | Jerzy |  | MK WL CS GC YZ JB PP TI BT GJ JE | Cerizza | GC
4/8/2016 22:00:00 | set Kyoto thresholds |  | Isobe | Lynch | Clem | Piotr |  | MK WL CS GC YZ JB PP TI BT GJ | Estee | JE
4/8/2016 23:00:00 | Make sure tuning is good and clean |  | Isobe | Lynch | Clem | Piotr |  | MK WL CS GC YZ JB TM PP TI BT | Lynch | WL
4/9/2016 0:00:00 | Make sure tuning is good and clean |  | Isobe | Lynch | Clem | Piotr |  | MK WL CS GC YZ JB TM PP TI BT | Santamaria | CS
4/9/2016 1:00:00 | Select optimal centrality trigger |  | Kaneko | Lynch | Clem | Piotr |  | MK WL CS GC YZ JB TM PP TI BT | Tsang | BT
4/9/2016 2:00:00 | Select optimal centrality trigger |  | Kaneko | Lynch | Clem |  |  | MK WL CS GC YZ JB TM | Suzuki | DS | SAMURAI | MK, HO, AI
4/9/2016 3:00:00 | Select optimal centrality trigger | ` | Kaneko | Lynch | Clem |  |  | MK WL CS GC YZ JB TM | Zhang | YZ | Electronics | WL, CS, PK
4/9/2016 4:00:00 | Select optimal centrality trigger | Giordano | Kaneko | Lynch |  |  |  | MK WL CS GC YZ JB TM | Isobe | TI | Kyoto | MK, TM
4/9/2016 5:00:00 | Select optimal centrality trigger (cross-section measurements) | Giordano | Kaneko | Lynch |  |  |  | MK WL CS GC YZ JB TM BT | Mizuki | MN | Katana | JL, PP, PL
4/9/2016 6:00:00 | Select optimal centrality trigger | Giordano | Suzuki | Lynch |  |  |  | DS GJ YZ BT TM | Tetsuya | TM | TPC | JB, MK, WL
4/9/2016 7:00:00 | Anode voltage & gain tests | Genie | Suzuki | Betty |  |  |  | DS GJ YZ BT | Kaneko | MK | GG | JE, HL, YZ
4/9/2016 8:00:00 | No beam | Genie | Suzuki | Betty |  |  |  | DS GJ YZ BT | Jhang | GJ | software | GC, GJ, JW
4/9/2016 9:00:00 | No beam | Genie | Suzuki |  |  |  | Justin | DS GJ JE | JW Lee | JW
4/9/2016 10:00:00 | No beam | Genie | Suzuki |  |  |  |  | DS GJ | HS Lee | HL
4/9/2016 11:00:00 | No beam | Genie | Mizuki |  |  |  |  | MN GJ | Shuji Nishimura | SN
4/9/2016 12:00:00 | No beam | Genie | Mizuki | Betty |  |  |  | MN BT | Jerzy | JL
4/9/2016 13:00:00 | No beam | Genie | Mizuki | Betty |  |  |  | MN BT | Piotr | PK
4/9/2016 14:00:00 | No beam | Genie | Isobe | Betty |  |  |  | MN BT | pawel | PL
4/9/2016 15:00:00 | No beam | Genie | Isobe | Betty |  |  |  | MN BT JE | Kristof | KP
4/9/2016 16:00:00 | No beam | Genie | Isobe | Betty |  |  |  | MN BT JE
4/9/2016 17:00:00 | No beam | Giordano | Kaneko | Lynch | Clem |  | JB YZ | MK BT CS | NeuLand | group
4/9/2016 18:00:00 | Katana Veto test | Giordano | Kaneko | Lynch | Clem |  | JB YZ | MK BT CS
4/9/2016 19:00:00 | Data taking for PID + gating grid test | Giordano | Kaneko | Lynch | Clem |  | JB YZ | MK BT CS
4/9/2016 20:00:00 | Data taking for PID | Giordano | Kaneko | Lynch | Clem |  | JB YZ | MK BT CS
4/9/2016 21:00:00 | Cobo gain test + RIBFDAQ debugging+Katana test | Giordano | Murakami | Lynch | Clem |  | JB YZ | TM WL
4/9/2016 22:00:00 | Data taking for PID with new ASAD gain map A bad drift time | Giordano | Murakami | Lynch | Clem |  | JB | TM WL
4/9/2016 23:00:00 | Data taking for PID with new ASAD gain map A bad drift time | Giordano | Murakami | Lynch | Clem |  | JB | TM WL
4/10/2016 0:00:00 | Data taking for PID with new ASAD gain map A+ AC trigger test | Giordano | Murakami | Lynch | Clem |  | JB | TM WL
4/10/2016 1:00:00 | Take gating grid noise data, 117 ns peaking time 10,000 events | Giordano | Murakami | Lynch | Clem |  | JB | TM WL
4/10/2016 2:00:00 | Cobo loading problem | Giordano | Murakami | Lynch | Clem
4/10/2016 3:00:00 | Cobo loading problem | Giordano | Murakami | Lynch | Clem
4/10/2016 4:00:00 | Data taking for PID with original ASAD gain | Giordano | Murakami | Betty | Clem
4/10/2016 5:00:00 | Katana testing | Giordano | Murakami | Betty | Clem |  | YZ | TM BT
4/10/2016 6:00:00 | Data taking for PID with original ASAD gain | Genie | Suzuki | Betty | Clem |  | YZ | DS BT
4/10/2016 7:00:00 | Data taking for PID with original ASAD gain | Genie | Suzuki | Betty | Clem |  | YZ | DS BT
4/10/2016 8:00:00 | Data taking for PID with original ASAD gain | Genie | Suzuki | Betty | Clem |  | YZ | DS BT
4/10/2016 9:00:00 | End of commissioning time | [6 empty] | DS BT
Please add your initials to the “Shifts by initials” column for times when you plan to be on shift

## Katana
KATANA & Trigger Box setting program
Beam time | Tasks | Beam | Total time | Responsibles
DACQ in the independent mode
20 | Beam sweep – collecting data to all VETO paddles – rough info on beam position | ON | 20 | Aki, Piotr & Jerzy
15 | TPC triggered by Start, collecting beam tracs Estimation of beam position at KATANA Setting TB gates Collecting AC data | ON | 35 | TPC group Jerzy Bill, Krzysztof & Clementine Piotr
15 | Setting KATANA in right position Setting AC thresholds | OFF | 50 | Jon & Jerzy Piotr
| Trigger box may be already used, except VETO |  | 18/02/1900
30 | Collecting VETO data (I) | ON | 20/03/1900 | Jerzy, Paweł & Piotr
5 | Changing KATANA position | OFF | 25/03/1900
30 | Collecting VETO data (II) | ON | 24/04/1900
5 | Changing KATANA position | OFF | 29/04/1900
30 | Collecting VETO data (III) | ON | 29/05/1900
10 | Setting VETO thresholds and gains | ON | 8/06/1900
| Now the trigger box is ready for use |  | 8/06/1900
5 | Change of DACQ configuration | ON | 13/06/1900 | Piotr
DACQ in the dependent mode

## Run Plan
Object | Responsible Persons | Date | Duration | Beam | Beam rate | Magnet status | Anode voltage | Target | St. Cnt. | KatanaV | KatanaM | KRATTA | Active veto | Kyoto | Busy OR | Data taking | Description
Insert Sn target | Jon/Mizuki | Before beam time | 0h 30min |  |  |  |  | 0.8 mm Sn
Beam tuning/check Katana (as much as possible) | Isobe/Murakami/BigRIPS | 2016-04-07 09:00 | 6:00 | 132Sn @ 300 MeV/u | 100 Hz | [11 empty] | Transport beam (Z~50) to TPC, beam rate: 1k.
Beam profile check (Also, Check where the beam is hitting Katana) | Lynch/Murakami | 4/7/2016 15:00:00 | 3:00 | 132Sn @ 300 MeV/u | 100 Hz |  | Low gain |  | Trigger | [7 empty] | Check beam profile with BDC, Check beam profile with TPC, confirm the position of trigger counter. Move them if needed.
Sweep magnetic field (depends on time constraint) | Isobe/Jerzy | 4/7/2016 18:00:00 | 0:00 |  |  | 0->0.5T | [10 empty] | Need run plan (Isobe/Jerzy)
Beam trajectory with magnet/Beam PID | Isobe/Lynch/Giordano | 4/7/2016 21:00:00 | 1:00 | 132Sn @ 300 MeV/u | 100 Hz | ON |  |  | Trigger | [6 empty] | Yes | https://indico2.riken.jp/indico/getFile.py/access?contribId=4&resId=1&materialId=slides&confId=2221
Timing test | Clementine/Lynch/Piotr | 4/7/2016 18:00:00 | 1:00 | 132Sn @ 300 MeV/u | 100 Hz | ON |  |  | Trigger | Veto | 1 |  | Veto | 1 | Veto | - | Verify timing
GGD tests | 1/Justin/HyoSang | 4/7/2016 19:00:00 | 2:00 | 132Sn @ 300 MeV/u | 100 Hz | ON |  |  | Trigger | [6 empty] | Yes? | https://docs.google.com/spreadsheets/d/1UAeDEBw7f1Zr9flBgYRSoDCEhSVmlDeXVp7POSwwoAI/edit?usp=sharing Scan the gating grid voltage to find optimum value. Verify performance of gating grid circuit and correct data as needed.
DAQ coupling test | Isobe/Togano | 4/7/2016 22:00:00 | 1:00 | 132Sn @ 300 MeV/u | 100 Hz | ON |  |  | Trigger | - | - | - | - | - | - | Yes | Coupling test of RIBF DAQ and GET DAQ
Busy DAQ test | Isobe/Lynch | 4/7/2016 23:00:00 | 1:00 | 132Sn @ 300 MeV/u | 100 Hz | ON |  |  | Trigger | - | - | - | - | - | Veto | Yes | Reference for analysis (effect of diverse triggers)
St. Cnt. Reference | Clementine | 4/8/2016 0:00:00 | 0:15 | 132Sn @ 300 MeV/u | 1 kHz | ON |  |  | Trigger | - | - | - | - | - | Veto | -
Kyoto test | Kaneko/Giordano | 4/8/2016 0:15:00 | 0:45 | 132Sn @ 300 MeV/u | >1 kHz | ON |  |  | Trigger | Veto | - | - | Veto | 1 | Veto | Yes | Check of KyotoM trigger
Katana V test for thresh | Katana | 4/8/2016 1:00:00 | 1:00 | 132Sn @ 300 MeV/u | 1 kHz | ON |  | 0.8 mm Sn | Trigger | Trigger | - | - | - | 2 | Veto | Yes | Varying threshold KatanaV
Active Collimator test for thresh | Katana | 4/8/2016 2:00:00 | 0:30 | 132Sn @ 300 MeV/u | 1 kHz | ON |  |  | Trigger | Trigger | - | - | - | 2 | Veto | Yes | Varying threshold KatanaV
Katana M test | Katana | 4/8/2016 2:30:00 | 0:30 | 132Sn @ 300 MeV/u | 1 kHz | ON |  |  | Trigger | Veto | - | - | - | 2 | Veto | Yes | Check of KatanaM trigger
Trigger test | Piotr/Clementine/Lynch | 4/8/2016 3:00:00 | 2:00 | 132Sn @ 300 MeV/u | 1 kHz | ON |  |  | Trigger | Veto | 1 | - | Veto | 1 | Veto | Yes | check electronic (need game plan to coordinate with check timing)
Anode voltage & gain tests | Justin/Bill/Giordano | 4/8/2016 5:00:00 | 2:00 | 132Sn @ 300 MeV/u | 1 kHz | ON | [10 empty] | Need game plan
Preparation to take data during Ota-san's beam | Clementine/Lynch | 2016-04-08 07:00 | 2:00 |  | 1 kHz | Turn OFF | [10 empty] | Need game plan
MT for Ota-san |  | 2016-04-08 09:00 |  |  | 1 kHz
Just take data | Hyo-Sang/Zhang Yan | 2016-04-08 06:10 | 5:00 | 132Sn @ 300 MeV/u | 1 kHz | OFF | Low gain |  | Trigger | [6 empty] | Yes
Peaking time test (117ns) | Isobe/Giordano | 2016-04-09 03:30 | 1:00 | 132Sn @ 300 MeV/u | 1 kHz |  |  |  | Trigger | Veto | 2 | - | Veto | 1 | Veto | Yes | Test with 2 shorter peaking times (117ns/70ns), take just enough data to have enough stat for analysis
End of Ota-san MT |  | 2016-04-09 15:00 |  |  | 1 kHz | OFF
Beam tuning/thick plastic counter | Isobe/Mizuki | 2016-04-09 03:40 | 6:00 | 132Sn @ 300 MeV/u | 1 kHz | [10 empty] | Yes | Replacement at BigRIPS of a thick plastic counter & use Katana paddle for start time (ask Bill and Jerzy)
Data taking w/thick plastic counter | Isobe/Mizuki | 2016-04-09 09:40 | 3:30 | 132Sn @ 300 MeV/u | 1 kHz |  |  |  | Trigger | Veto | 2 | - | Veto | 1 | Veto | Yes
Particle Identification | Lynch/Giordano/Isobe | 2016-04-07 23:40 | 6:00 | 132Sn @ 300 MeV/u | 1 kHz | ON |  | ??? |  |  | 1 | - |  | 0 | Veto | Yes | . i. Make Z:1~3 particle with BigRIPS. Check dE/dX and tracking of the Z:1~3 or light beam. use Katana as start time
Variation of rigidity settings (changing beam energy) | Isobe/Lynch/Giordano | 2016-04-08 22:30 | 5:00 | 132Sn @ 300 MeV/u | 1 kHz | [10 empty] | Yes | 3~5 rigidity settings & effect on PID
Central collision without magnet? | Isobe
End of commissioning time |  | 2016-04-09 15:00
Tests Pre-Ota-san |  | 4/8/2016 5:00:00 | 24:00:00
Tests TOTAL |  | 4/9/2016 15:00:00 | 20:30:00
30:00:00
https://docs.google.com/spreadsheets/d/1tOC5q_Wo95WKVLpNtxosGxet9kW477sfCe7ighAYuIw/pubhtml

## Sweeping
0. B=0T, beam trajectory is at the center of beam line.
1. Turn on TPC HV to low gain setting:
2. Trigger is beam only made by backup trigger logic.
3. Start to take data.
4. Start to sweep the magnet.
5. Stop to take data after sweeping is finished.
6. Try to move the beam hit position by 1.5cm off.

## Shifts
Date | Object | shifts | BigRIPS/Kyoto | Electronics |  | Katana | GG | Software | Shifts by initials
Before beam time | Insert Sn target | [7 empty] | JB | Name | Code
Before beam time | DAQ coupling test | Isobe | [6 empty] | TI GC | Barney | JB
Before beam time | Busy DAQ test | Isobe | [6 empty] | TI GC | Cerizza | GC
2016-04-07 12:30 | Beam tuning/check Katana (as much as possible) | Isobe | Tetsuya | Lynch |  | Jerzy |  |  | BT JE JB TI YT TM GC | Estee | JE
2016-04-08 00:30 | Beam profile check (Also, Check where the beam is hitting Katana) | Isobe | Tetsuya | Lynch |  | Jerzy |  | Giordano | BT JE JB TI YT TM GC GJ JW | Lynch | WL
4/8/2016 1:30:00 | Beam Profile; Sweep magnetic field | Isobe | Tetsuya | Lynch |  | Jerzy | Justin | Giordano | BT JE JB TI YT GC GJ JW | Santamaria | CS
4/8/2016 2:30:00 | Beam Profile; Sweep magnetic field | Isobe | Tetsuya | Lynch |  | Jerzy | Justin | Giordano | BT JE JB TI YT GC GJ JW | Tsang | BT
4/8/2016 3:30:00 | Beam trajectory with magnet/Beam PID | Isobe | Tetsuya | Lynch | Clem | Katana | Justin |  | JE HL GC JW CS | Suzuki | DS
4/8/2016 4:30:00 | Timing test |  | Tetsuya | Lynch | Clem | Piotr | Justin |  | TI YT DS CS | Zhang | YZ
4/8/2016 5:30:00 | GGD tests |  | Tetsuya | Lynch | Clem | Katana | Justin |  | JE HL GC JW YZ | Isobe | TI
4/8/2016 6:30:00 | GGD tests |  | Tetsuya | Lynch | Clem | Katana | Justin |  | JE HL GC JW YZ | Mizuki | MN
4/8/2016 7:30:00 | DAQ coupling test | Isobe | Tetsuya |  | Clem | Katana |  |  | GC CS | Tetsuya | TM
4/8/2016 8:30:00 | Busy DAQ test | Isobe | Tetsuya |  | Clem | Katana |  |  | GC CS | Kaneko | MK
[9 empty] | TM CS | Jhang | GJ
2016-04-08 09:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | SAMURAI | MK, HO, AI
4/8/2016 10:00:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | Electronics | WL, CS, PK
4/8/2016 11:00:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | Kyoto | MK, TM
4/8/2016 12:00:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | Katana | JL, PK, PL
4/8/2016 13:00:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | TPC | JB, MK, WL
4/8/2016 14:00:00 | MT for Ota-san |  | Suzuki | [5 empty] | DS | GG | JE, HL, YZ
4/8/2016 15:00:00 | check beam, Kyoto trigger test |  | Suzuki |  | Clem | Katana |  | Genie | BT GC GJ JE MK CS | software | GC, GJ, JW
4/8/2016 16:00:00 | set Katana veto thresholds |  | Suzuki |  | Clem | Katana |  | Genie | CS | JW Lee | JW
4/8/2016 17:00:00 | Active Collimator test for thresh;; Katana M |  | Suzuki |  | Clem | Katana |  | Genie | CS | HS Lee | HL
4/8/2016 16:00:00 | Trigger test (May not need) |  | Kaneko | Lynch | Clem | Piotr |  | Genie | MK TM YZ CS
4/8/2016 17:00:00 | Trigger test (May not need) |  | Kaneko | Lynch | Clem | Piotr |  | Genie | MK TM YZ CS
4/8/2016 18:00:00 | Anode voltage & gain tests |  | Kaneko | Lynch | Clem |  | Justin | Giordano | BT JE MK TM GC CS
4/8/2016 19:00:00 | Anode voltage & gain tests |  | Kaneko | Lynch | Clem |  | Justin | Giordano | BT JE MK TM GC CS
4/8/2016 20:00:00 | Peaking time test (117 ns) |  |  | Betty |  |  |  | Genie | TM YZ
4/8/2016 21:00:00 | Data taking for PID |  |  | Betty |  |  |  | Genie | TM YZ
4/8/2016 22:00:00 | Data taking for PID |  |  | Betty |  |  |  | Genie | TM YZ
4/8/2016 23:00:00 | Data taking for PID |  |  | Betty |  |  |  | Genie | TM YZ
4/9/2016 0:00:00 | Data taking for PID |  |  | Betty |  |  |  | Genie | TM YZ
4/9/2016 1:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | [5 empty] | TI TM JB
4/9/2016 2:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | [5 empty] | TI TM
4/9/2016 3:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | [5 empty] | TI TM
4/9/2016 4:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | [5 empty] | TI TM
4/9/2016 5:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | [5 empty] | TI TM GC JE
4/9/2016 6:00:00 | Beam tuning/thick plastic counter |  | Tetsuya | Lynch |  |  |  | Giordano | TI TM GC
4/9/2016 7:00:00 | Tuning w Z=1-3 PID |  | Tetsuya | Lynch |  |  |  | Giordano | TI TM GC JE JW
4/9/2016 8:00:00 | Tuning w Z=1-3 PID |  | Tetsuya | Lynch |  |  |  | Giordano | TI TM GC JE JW
4/9/2016 9:00:00 | Tuning w Z=1-3 PID | Isobe | Tetsuya | Lynch |  |  |  | Giordano | TI TM GC GJ JE JW
4/9/2016 10:00:00 | Change energy 3 Brho setting | Isobe | Kaneko | Lynch |  |  |  | Giordano | BT MK TI GC GJ JE JW
4/9/2016 11:00:00 | Change energy 3 Brho setting | Isobe | Kaneko | Lynch |  |  |  | Giordano | BT MK TI GC GJ JE JW
4/9/2016 12:00:00 | Change energy 3 Brho setting | Isobe | Kaneko |  |  |  |  | Giordano | BT MK TI GC GJ JW
4/9/2016 13:00:00 | Contingency catch up | Isobe | Kaneko |  |  |  |  | Giordano | BT MK TI GC GJ JW
4/9/2016 14:00:00 | Contingency catch up | Isobe | Kaneko |  |  |  |  | Giordano | BT MK TI GC GJ JW
4/9/2016 15:00:00 | Contingency catch up | Isobe | Kaneko |  |  |  |  | Giordano | BT MK TI GC GJ JW
2016-04-10 09:00 | End of commissioning time
2016-04-09 18:00 | Dinner
2016-04-09 15:00 | Tests TOTAL
Please add your initials to the “Shifts by initials” column for times when you plan to be on shift