## Sheet1
Dates |  |  |  |  | Names | Japan | Korea | UK | MSU | Dates | TAMU | China | GANIL
2013-04-01 | Monday | P.O. for drivers |  |  |  | Aki/Nori | Genie |  |  | 2013-04-01
2013-04-02 | Tuesday | P.O for feed-throughs |  |  |  | Aki/Nori | Genie |  |  | 2013-04-02
2013-04-03 | Wednesday | P.O. for insulator flange and bolts |  |  |  | Aki/Nori | Genie |  |  | 2013-04-03
2013-04-04 | Thursday |  | DAQ |  |  | Aki/Nori | Genie |  |  | 2013-04-04
2013-04-05 | Friday |  | online/offline analysis |  |  | Aki/Nori | Genie |  |  | 2013-04-05
2013-04-06 | Saturday |  |  |  |  | Aki/Nori | Genie |  |  | 2013-04-06
2013-04-07 | Sunday |  |  |  |  | Aki/Nori | Genie |  |  | 2013-04-07
2013-04-08 | Monday | All chamber parts will be shipped from MSU |  |  |  | Aki/Nori | Genie |  |  | 2013-04-08
2013-04-09 | Tuesday |  |  |  |  | Aki/Nori | Genie |  |  | 2013-04-09
2013-04-10 | Wednesday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-10
2013-04-11 | Thursday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-11
2013-04-12 | Friday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-12
2013-04-13 | Saturday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-13
2013-04-14 | Sunday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-14
2013-04-15 | Monday | Test MSU chamber parts |  |  |  | Aki/Nori |  |  |  | 2013-04-15
2013-04-16 | Tuesday | pump chamber |  |  |  | Aki/Nori |  |  |  | 2013-04-16
2013-04-17 | Wednesday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-17
2013-04-18 | Thursday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-18
2013-04-19 | Friday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-19
2013-04-20 | Saturday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-20
2013-04-21 | Sunday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-21
2013-04-22 | Monday | delivery of translation plate adapters to bottom flange ("orange pieces") |  |  |  | Aki/Nori |  |  |  | 2013-04-22
2013-04-23 | Tuesday | Mount bottom plate with translation plate |  |  |  | Aki/Nori |  |  |  | 2013-04-23
2013-04-24 | Wednesday | Mount flanges for M-Ball and scintillator |  |  |  | Aki/Nori |  |  |  | 2013-04-24
2013-04-25 | Thursday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-25
2013-04-26 | Friday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-26
2013-04-27 | Saturday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-27
2013-04-28 | Sunday |  |  |  |  | Aki/Nori |  |  |  | 2013-04-28
2013-04-29 | Monday | Holiday in Japan |  |  |  | Aki/Nori |  |  |  | 2013-04-29
2013-04-30 | Tuesday | Holiday in Japan |  |  |  | Aki/Nori |  |  |  | 2013-04-30
2013-05-01 | Wednesday | Holiday in Japan |  |  |  | Aki/Nori |  |  |  | 2013-05-01
2013-05-02 | Thursday | Holiday in Japan |  |  |  | Aki/Nori |  |  |  | 2013-05-02
2013-05-03 | Friday | Holiday in Japan |  |  |  | Aki/Nori |  |  |  | 2013-05-03
2013-05-04 | Saturday |  |  |  |  | Aki/Nori |  |  |  | 2013-05-04
2013-05-05 | Sunday |  |  |  |  | Aki/Nori |  |  |  | 2013-05-05
2013-05-06 | Monday |  |  |  |  | Aki/Nori |  |  |  | 2013-05-06
2013-05-07 | Tuesday |  |  |  |  | Aki/Nori |  |  |  | 2013-05-07
2013-05-08 | Wednesday |  |  |  |  | Aki/Nori |  |  |  | 2013-05-08
2013-05-09 | Thursday |  |  |  |  | Aki/Nori |  | Will |  | 2013-05-09
2013-05-10 | Friday |  |  |  |  | Aki/Nori |  | Will |  | 2013-05-10
2013-05-11 | Saturday |  |  |  |  | Aki/Nori |  | Will |  | 2013-05-11
2013-05-12 | Sunday |  |  |  |  | Aki/Nori |  | Will |  | 2013-05-12
2013-05-13 | Monday |  |  | ***transportation of beam tuning detector, microball (Rachel, Lauren) |  | Aki/Nori |  | Will | Rachel | 2013-05-13 | Lauren/Sherry
2013-05-14 | Tuesday | test of bottom plate alignment (Rachel) | vacuum leak test (at SAMURAI area): Aki, Will |  |  | Aki/Nori |  | Will | Rachel | 2013-05-14 | Lauren/Sherry
2013-05-15 | Wednesday | setup microball to 2 bars, check that beam counter works | assembly of target flange, m-ball table, scintillator flange (Aki, Rachel) | ***remote target driver, remote DS driver, targt ladder delivered |  | Aki/Nori |  | Will | Rachel | 2013-05-15 | Lauren/Sherry
2013-05-16 | Thursday | setup microball, beam counter, electronics in chamber (Rachel, Lauren) | test chamber closing with O-ring and lifting by crank (Aki) |  |  | Aki/Nori |  | Will | Rachel | 2013-05-16 | Lauren/Sherry
2013-05-17 | Friday | test chamber alignment (Rachel) | test remote control (Aki) | DS: supply HV and see dark current pedestal (Lauren) |  | Aki/Nori |  | Will | Rachel | 2013-05-17 | Lauren/Sherry
2013-05-18 | Saturday |  |  |  |  | Aki/Nori |  | Will | Rachel | 2013-05-18 | Lauren
2013-05-19 | Sunday |  |  |  |  | Aki/Nori |  | Will | Rachel | 2013-05-19 | Lauren
2013-05-20 | Monday | Find electronics, crates, cables (Rachel, Will) | chamber leak test (Aki) | ***DS delivered |  | Aki/Nori |  | Will | Rachel | 2013-05-20
2013-05-21 | Tuesday |  | scintillator (DS) offline test (Will, Aki) |  |  | Aki/Nori |  | Will | Rachel | 2013-05-21
2013-05-22 | Wednesday |  |  | ***transportation of microball electronics (Jack) |  | Aki/Nori |  | Will | Rachel/Jack | 2013-05-22
2013-05-23 | Thursday |  |  |  |  | Aki/Nori |  | Will | Rachel/Jack | 2013-05-23
2013-05-24 | Friday | Test m-ball and readout with V792modules | microball DAQ standalone setting and test (Aki, Will) | Microball offline test, check ADC pedestal (Rachel, Jack) |  | Aki/Nori |  | Will/Janet | Rachel/Jack | 2013-05-24
2013-05-25 | Saturday | Test m-ball and readout with V792modules |  | Make/check Microball mapping (Rachel, Jack) |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack | 2013-05-25
2013-05-26 | Sunday | Test m-ball and readout with V792modules | clean up F8 area |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack | 2013-05-26 | Alan | Fei Lu
2013-05-27 | Monday | Lift chamber and electronics to F8 area (Aki) | online analysis (Janet) |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack | 2013-05-27 | Alan | Fei Lu | Abdou
2013-05-28 | Tuesday | chamber, microball alignment to beamline (Rachel) | set up electronics (Jack) | ***second set of Sn targets delivered (Tetsuya) |  | Aki/Nori/Tetsuya | Genie | Will/Janet | Rachel/Jack | 2013-05-28 | Alan | Fei Lu | Abdou
2013-05-29 | Wednesday | test remote control & chamber vacuum (Aki) | set up electronics (Jack) |  |  | Aki/Nori/Tetsuya | Genie | Will/Janet | Rachel/Jack/Bill/Justin | 2013-05-29 | Alan | Fei Lu | Abdou
2013-05-30 | Thursday |  |  |  |  | Aki/Nori/Tetsuya | Genie | Will/Janet | Rachel/Jack/Bill/Justin | 2013-05-30 | Alan | Fei Lu | Abdou
2013-05-31 | Friday |  |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Bill/Justin | 2013-05-31 | Alan | Fei Lu | Abdou
2013-06-01 | Saturday |  |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-01 | Alan | Fei Lu | Abdou
2013-06-02 | Sunday |  |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-02 | Alan | Fei Lu | Abdou
2013-06-03 | Monday | DAQ |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-03 | Alan | Fei Lu | Abdou
2013-06-04 | Tuesday | online analysis |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-04 | Alan | Fei Lu/Zhang | Abdou
2013-06-05 | Wednesday | offline analysis |  |  |  | Aki/Nori | Genie | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-05 | Alan | Fei Lu/Zhang | Abdou
2013-06-06 | Thursday |  |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-06 |  | Fei Lu/Zhang | Abdou
2013-06-07 | Friday |  |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Justin | 2013-06-07 |  | Fei Lu/Zhang | Abdou
2013-06-08 | Saturday | finish to access F8, start to tune the beam with BigRIPS |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Justin/Bill | 2013-06-08 | Andrew | Fei Lu/Zhang | Abdou
2013-06-09 | Sunday |  |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Justin/Bill | 2013-06-09 | Andrew | Fei Lu/Zhang | Abdou
2013-06-10 | Monday |  |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Justin/Bill | 2013-06-10 | Andrew | Fei Lu/Zhang | Abdou
2013-06-11 | Tuesday | experiment |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Bill/Justin | 2013-06-11 | Andrew | Fei Lu/Zhang/Xiao
2013-06-12 | Wednesday | experiment |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Bill/Justin | 2013-06-12 | Andrew | Fei Lu/Zhang/Xiao
2013-06-13 | Thursday | experiment |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Bill/Justin | 2013-06-13 | Andrew | Fei Lu/Zhang/Xiao
2013-06-14 | Friday | experiment |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Bill/Justin | 2013-06-14 | Andrew | Fei Lu/Zhang/Xiao
2013-06-15 | Saturday | experiment |  |  |  | Aki/Nori/Tetsuya | Genie/Byungsik | Will/Janet | Rachel/Jack/Betty/Bill/Justin | 2013-06-15 | Andrew | Fei Lu/Zhang/Xiao
2013-06-16 | Sunday | cleanup |  |  |  | Aki/Nori | Genie/Byungsik | Will | Rachel/Jack/Justin | 2013-06-16 | Andrew | Fei Lu/Zhang/Xiao
2013-06-17 | Monday | cleanup |  |  |  | Aki/Nori | Genie | Will | Rachel/Jack/Justin | 2013-06-17 |  | Fei Lu/Zhang/Xiao
2013-06-18 | Tuesday | cleanup |  |  |  | Aki/Nori | Genie | Will | Rachel/Jack/Justin | 2013-06-18
2013-06-19 | Wednesday | packing |  |  |  | Aki/Nori | Genie | Will |  | 2013-06-19
2013-06-20 | Thursday | packing |  |  |  | Aki/Nori | Genie | Will |  | 2013-06-20
2013-06-21 | Friday |  |  |  |  | Aki/Nori | Genie | Will |  | 2013-06-21
2013-06-22 | Saturday |  |  |  |  | Aki/Nori | Genie | Will |  | 2013-06-22
2013-06-23 | Sunday |  |  |  |  | Aki/Nori | Genie | Will | Betty/Bill | 2013-06-23
2013-06-24 | Monday | collaboration days |  |  |  | Aki/Nori | Genie | Will | Betty/Bill | 2013-06-24
2013-06-25 | Tuesday | collaboration days |  |  |  | Aki/Nori | Genie | Will | Betty/Bill | 2013-06-25
2013-06-26 | Wednesday | RIBF Users meeting |  |  |  | Aki/Nori | Genie | Will | Rachel/Betty/Bill | 2013-06-26
2013-06-27 | Thursday | RIBF Users meeting |  |  |  | Aki/Nori | Genie | Will | Rachel/Betty/Bill | 2013-06-27
2013-06-28 | Friday | RIBF NP-PAC |  |  |  | Aki/Nori | Genie |  | Betty/Bill | 2013-06-28
2013-06-29 | Saturday | RIBF NP-PAC |  |  |  | Aki/Nori | Genie |  | Betty/Bill | 2013-06-29
2013-06-30 | Sunday |  |  |  |  | Aki/Nori | Genie |  |  | 2013-06-30